## Valuation
Item No | Description | Unit | Contract Qty | Rate | Contract Amount | Previous Qty | Previous Amount | Claimed Qty | Claimed Amount | Category
Prelim.1 | Site establishment and preliminaries (provisional) | Sum | 1 | 850000 | 850000 | 0 | 0 | 0 | 0 | preliminaries
A.1.1 | Excavation for foundation in soft material | m3 | 1200 | 185 | 222000 | 0 | 0 | 0 | 0 | works
A.2.1 | Grade C40 concrete to pile caps | m3 | 480 | 1420 | 681600 | 0 | 0 | 0 | 0 | works
A.2.2 | Formwork to pile caps | m2 | 1600 | 290 | 464000 | 0 | 0 | 0 | 0 | works
A.3.1 | High yield reinforcement bars to pile caps | kg | 95000 | 12.8 | 1216000 | 0 | 0 | 0 | 0 | works
B.1.1 | Grade C35 concrete to ground floor slab | m3 | 620 | 1280 | 793600 | 0 | 0 | 0 | 0 | works
B.2.1 | Brick wall 100mm internal | m2 | 3500 | 310 | 1085000 | 0 | 0 | 0 | 0 | works
B.3.1 | Ceramic wall tiles to toilets | m2 | 1800 | 420 | 756000 | 0 | 0 | 0 | 0 | works
C.1.1 | MVAC ductwork (provisional) | Sum | 1 | 2200000 | 2200000 | 0 | 0 | 0 | 0 | mep
C.2.1 | Electrical containment and cable tray | m | 4200 | 95 | 399000 | 0 | 0 | 0 | 0 | mep
B.2.1A | Brick wall 100mm internal — additional claim | m2 | 3500 | 310 | 1085000 | 0 | 0 | 0 | 0 | works
V.01 | VO-12 Extra concrete to transfer beam | m3 | 40 | 1550 | 62000 | 0 | 0 | 0 | 0 | variation
V.02 | Additional night works premium | Sum | 1 | 180000 | 180000 | 0 | 0 | 0 | 0 | variation
MOS.1 | Materials on site - reinforcement steel | Sum | 1 | 320000 | 320000 | 0 | 0 | 0 | 0 | materials_on_site
A.2.1X | Grade C40 concrete to pile caps — remeasurement | m3 | 100 | 1420 | 142000 | 0 | 0 | 0 | 0 | works